## Sheet1
Week | Date | Planned work | Work done | Supervisor feedback
June/July holidays |  | Implement initial software system. | Implemented basic system using Q-numbers.
1 | 2021-08-09 | Refactor to floating point. | Refactored Q-number code to floating point. | 2021-08-11 | Initial meeting to discuss Skripsie approach
2 | 2021-08-16 | Start block diagrams. Debug. | Halfway done block diagrams. Debugged current code. More refactoring. | 2021-08-18 | Agreement between skripsie student and study leader regarding mutual responsibilities
3 | 2021-08-23 | Block diagrams. Design documentation. | Almost done with block diagrams. Design documentation started. | 2021-08-20 | Meeting to discuss mathematical description of skripsie topic
4 | 2021-08-30 | Start literature overview. | Literature overview started. Started work on waveshaping. | 2021-08-29 | Alternatives to STM32 implementation mentioned.
5 | 2021-09-06 | Conduct basic tests. Work on full system. | Conducted some tests. Debugging. MATLAB simulation of waveshaping. | 2021-09-06 | Mixed version of 4 tracks resulting from the software. Spectograms of a tanh(G*sin(2pi*f)) distortion, with a frequency sweep of 20 to 20kHz. Anti-aliasing strategy. Mentioned possible scope reduction.
6 | 2021-09-13 | Documentation and debugging. Work on MIDI library integration. | Documentation. More system debugging. Full MIDI library integration.
7 | 2021-09-20 | Refactor code to avoid data duplication. Documentation. | Refactored code. Rewrote parts for efficiency. Added waveshaping support. | 2021-09-27 | Code for predifined LUTs. Master design for software. Software is complex, intensive, and can fill up the entire report - SCOPE CHANGED TO EXCLUDE STM32 IMPLEMENTATION.
8 | 2021-09-27 | Start system tests. MATLAB analysis code. | MATLAB analysis code. Started basic system tests. Shortened report. Report length too long.
9 | 2021-10-04 | Debugging. | Debugging. System is mostly operational.
10 | 2021-10-11 | Debug. Generate test audio. Identify further problems. | Generated test audio. Better system interface added. Better waveshaping. | 2021-10-12 | Additional audio track. Skripsie progress. Report format not up to standard. Must change report orginisation.
11 | 2021-10-18 | Reorganise report. | Reorganised report. Continued work on documentation. Shortened report.
12 | 2021-10-25 | System tests and analysis. | System testing and documentation.
13 | 2021-11-01 | System tests and analysis. Work on testing documentation | Conducted interviews for final test. Updated figures and testing documentation.
14 | 2021-11-08 | Report writing. | Finished report. Commence editing, and prepare presentation. | 2021-11-09 | Feedback on the entirety of skripsie project
15 | 2021-11-15 | Hand in. Work on poster and video.
Formulas:
Date = [Date, row above]+7